## Schedule of works
Item | Description
1 | PREPARATION
Provide site setup, welfare facilities, temporary services and site security for the duration of the works.
Provide scaffolding and access to the extension and existing roof perimeter, including access for external wall insulation and roof tiling works.
Provide skips and removal of non-hazardous construction waste for the duration of the works. Hazardous waste including asbestos removal is excluded and subject to the Refurbishment & Demolition asbestos survey.
2 | DEMOLITION
Demolish the existing garage (approximately 48m2) including foundations, floor slab and roof. Set aside and stack the garage wall stone on site for the client's re-use in the garden walls and planters, and set aside sound roof tiles for re-use on the new pitched roof.
Demolish the existing UPVC and glass conservatory (approximately 15.5m2) including base and floor slab.
Remove the existing fireplace and chimney breasting as shown on drawing 2526329/SK02, and cap the existing chimney at ceiling level. Provide temporary support to the chimney stack above until the new support steelwork is installed.
Take down the existing non load bearing partitions shown for removal on the proposed ground floor plan, including the partitions to the existing utility, shower room and hall re-planning.
Strip out the existing utility room fittings, worktops, appliances and redundant service connections.
Strip out the existing shower room including sanitary fittings, wall and floor finishes and redundant service connections.
Strip out the existing bathroom including sanitary fittings, wall and floor finishes and redundant service connections for refitting.
Strip out the existing kitchen units, worktops, sink and appliances to allow the new opening to the dining room and the kitchen refit. Disposal of fridges and freezers is excluded; the householder arranges removal through the local council.
Form the widened opening between the kitchen and the new dining room in the existing external wall, including cutting out, needling and propping as required and making good reveals with fully bonded dense concrete common bricks (min. 20.0 N/mm2).
Form the new door and window openings in the existing external walls to the porches and link as shown, including cutting out, needling and propping as required and making good reveals with fully bonded dense concrete common bricks (min. 20.0 N/mm2).
Block up the existing openings identified on the proposed ground floor plan, in blockwork tied to the existing masonry with Furfix stainless steel wall starters.
Cut the existing roof truss rafters back to the wallplate at the rear extension junction and ensure the existing trusses are mechanically fixed to the wallplate.
Take up the existing patio paving carefully and set aside on site for re-use.
Fell and remove the tree adjacent to the house identified for removal on the proposed ground floor plan, and grub out the root system.
3 | EXCAVATIONS
Strip topsoil, vegetation and deleterious material to a minimum depth of 150mm and carry out reduced level excavation to the extension footprints, and remove spoil from site.
Excavate foundation trenches to the new extension external and internal walls and to the wind post foundation, keeping excavations free of water, loose material and soil. The price allows for normal excavatable ground and foundations to a maximum depth of 900mm. Any further depth or rock removal required will incur additional cost.
Excavate trenches for the new below ground foul drainage serving the en-suite and utility.
Excavate for the new rainwater drainage runs and soakaway.
Excavate the perimeter perforated land drain trench around the extensions and existing house.
4 | DRAINAGE
Extend and alter the existing below ground foul drainage to serve the new en-suite and utility room, including connection to the existing manhole, testing and making good.
Provide new rainwater drainage from the extension roofs and existing roof to a new soakaway. No surface water is to discharge directly or indirectly to the public sewerage system.
Provide perforated land drain in shingle to the perimeter of the extensions and existing house as shown on the 1:10 junction details.
Provide a channel drain to the sliding door threshold, including drainage spigot connected to the surface water drainage system.
5 | FOUNDATIONS
Provide minimum 650 x 225mm deep GEN 3 mass concrete strip foundations to the new external 365mm cavity blockwork walls, cast central under load bearing walls on suitable bearing strata and approved by the appointed Building Inspector prior to the concrete pour. Foundations to be stepped in accordance with Diagram 21 of the Approved Document where required, using C8/10 (GEN 1) mass concrete fill to achieve required bearing levels.
Provide minimum 450 x 225mm deep GEN 3 mass concrete strip foundation to the new internal 100mm thick blockwork wall, cast central under the load bearing wall.
6 | BELOW DPC
Provide footing blockwork below DPC to the extension walls in minimum 7.0N/mm2 blocks (Monacrete 100S by Mona Precast, or similar approved) with mortar designation III, tied to the existing masonry using Furfix stainless steel vertical wall starters and fixings.
Provide damp proof course to all new walls, positioned a minimum of 150mm above external ground level, and lapped to the floor damp proof membrane.
Provide 50mm cavity insulation to the substructure cavity, installed to a minimum 225mm below top of floor level, with wall insulation carried below the floor insulation line, and concrete cavity fill to prevent cavity collapse.
Provide sub-floor ventilation to the suspended floor voids using proprietary ventilation sleeves and air bricks at maximum 2m centres and within 450mm of corners, giving a minimum of 1500mm2 of ventilation per metre run of external wall, sleeves sloped to the external face of the wall.
7 | GROUND FLOOR
Provide 150mm crushed stone base and levelling to the extension sub-floor voids, maintaining a minimum 150mm ventilated void below the underside of the floor.
Provide new suspended timber ground floors to the extensions: minimum 47 x 200mm deep C16 joists at maximum 400mm centres on joist hangers, with damp proof course membrane under joists, 150mm Ecotherm Eco-Versal insulation between joists, vapour control layer over, plywood/OSB decking and 25mm perimeter insulation, to achieve a floor U-value of 0.15 W/m2K or better.
Provide minimum 47 x 200mm deep C16 timber wall bearers fixed to the existing masonry with M12 chemical anchors (R-KEM resin anchors by Rawlplug, or similar approved) at maximum 450mm horizontal centres to the dining room floor, and at maximum 900mm horizontal centres to the link floor, anchors set central within masonry units.
Provide underfloor heating pipework within aluminium diffuser plates to the new suspended floors, laid ready to receive the floor finishes.
Provisional: take up the existing kitchen floor, install underfloor heating and Ecotherm insulation between the existing joists and reinstate the deck.
8 | WALLS
Provide new 365mm external cavity blockwork walls to the extensions: solid 7.3N/mm2 inner leaf and hollow outer leaf blockwork, stainless steel wall ties at 450mm vertical x 750-900mm horizontal centres, 50mm residual cavity with 115mm Ecotherm Eco-Cavity insulation, to achieve an external wall U-value of 0.18 W/m2K or better. New walls tied to existing masonry with Furfix stainless steel vertical wall starters.
Provide new internal load bearing solid blockwork partition (minimum 7.0N/mm2 blocks) on the strip foundation, as shown on drawing 2526329/SK02.
Provide new internal timber stud partitions to the extension layout and the internal re-planning, fully filled with acoustic Rockwool insulation.
9 | STRUCTURAL MEMBERS
Supply and install 2/ 178 x 102 x 19 UB beams as Beam (B.06), bolted together with M12 (Gr4.6) bolts and 48.3 x 3.2 CHS spacer tubes at maximum 600mm centres, over the maximum 3000mm opening, including temporary support to the existing structure until packed tight under the existing masonry with drypack mortar.
Supply and install 152 x 89 x 16 UB ridge beams (R/B.01) and (R/B.02) to the pitched extension roofs, including the full depth 6mm MS end plate splice connection with 2/ M16 (Gr8.8) bolts, and timber packers bolted to the UB web with M12 (Gr4.8) bolts at 600mm staggered centres.
Supply and install 152 x 89 x 16 UB roof/eaves beams (B.01) and (B.02), including timber wallplate and packers fixed to the UB with M12 (Gr4.8) bolts at 600mm centres.
Supply and install 152 x 89 x 16 UB Beam (B.03) supporting the roof/eaves beams (B.01) and (B.02).
Supply and install 152 x 89 x 16 UB Beams (B.04) and (B.05) as chimney stack support, set above ceiling level, with 6mm MS end plate connection and 2/ M16 (Gr8.8) bolts, Beams (B.05) bearing onto the outer UB of Beam (B.06) with no wallplate.
Supply and install 152 x 89 x 16 UB return tie beam (B.07) with minimum 350 x 6mm thick MS ledger plate welded to the UB bottom flange (6FW, 150mm hit/miss), including 100 x 120 x 6mm MS fin plate connection with 2/ M16 (Gr8.8) bolts to the wind post.
Supply and install 100 x 100 x 5.0 SHS wind post to the rear link wall, capped with 6mm MS plate, on a minimum 200 x 200 x 10mm MS baseplate with 4/ M12 chemical anchors (R-KEM II by Rawlplug, or similar approved) on minimum 15mm non-shrink grout bolted to the mass concrete strip foundation, and tied to the cavity blockwork with stainless steel flexible end frame cramps at maximum 225mm vertical staggered centres with neoprene isolation washers and patches.
Provide minimum 500 x 200 x 150mm deep C28/35 cast in-situ mass concrete padstones (P1) set onto the existing masonry at all beam bearings shown on drawing 2526329/SK02.
Provide minimum 330 x 100 x 140mm deep C28/35 precast concrete padstones/lintels set onto the existing masonry at the locations shown on drawing 2526329/SK02.
Provide standard duty 'L1/S' cavity lintels (by IG Lintels, or similar approved) to all new external wall openings to the front and rear extensions, with minimum 150mm end bearings, minimum 665mm returns where shown, insulated cavity closer and cavity tray to weep holes at maximum 450mm centres with a minimum of 2 per opening.
Provide 'R15A' 100 x 140mm deep pre-stressed concrete lintels (by Stressline Lintels, or similar approved) to all internal wall openings, with minimum 150mm end bearings.
Provide doubled up flat roof joists (minimum 2/ 47 x 150mm deep C24 timbers) as trimmers to the link rooflight, bolted together with M12 (Gr4.6) bolts and 50 x 50 x 2.5mm square washers at maximum 600mm centres.
Apply corrosion protection to the structural steelwork: blast clean to ISO Sa 2½ and apply minimum 80 microns DFT epoxy zinc phosphate primer to internal steelwork, with an additional coat of bitumen paint to steelwork in cavities or bearing on external solid masonry; galvanise all external steelwork to BS EN 1461.
10 | OPENINGS
Supply and install the external windows and doors scheduled on drawing SH.01: 13 no. white UPVC double-glazed windows and 3 no. white UPVC double-glazed external doors (including the 3000 x 2100mm sliding door), minimum U-value 1.2 W/m2K with low-e inner pane, manufactured to PAS 24:2022, fitted by a FENSA approved contractor with manufacturer's standard ironmongery. Include trickle ventilators (minimum 8,000mm2 equivalent area to habitable rooms, 4,000mm2 to wet rooms), safety glazing to critical locations to BS EN 12600, and 10mm perimeter tolerance gap filled with expanding foam.
Supply and install 1 no. rooflight (SL-00-01) to the link flat roof, on treated softwood insulated timber upstand set to a minimum 3 degree pitch, with vapour control layer, waterproof membrane lapped under the glazing unit flashing, and gasket and sealant under the glazing unit fixing.
11 | ROOF
Provide new pitched roof structure to the rear extension: minimum 47 x 150mm deep C24 rafters at maximum 400mm centres with 11mm OSB/3 sarking, timber noggins minimum 3/4 rafter depth at supports, ridge fillet, birds-mouth joints over the ridge plate, Simpson Strong-Tie SPR50 slope adjustable hangers where required, and wallplate with holding down straps.
Provide new flat roof structure: minimum 47 x 150mm deep C24 joists at maximum 400mm centres with timber noggins at supports, timber firrings designed to 1:40 falls, and 18mm plywood deck. New flat roof joists to bear onto the existing wallplate and be bolted to the existing roof trusses at intersection points with single M12 (Gr4.6) bolts, and to cantilever over to form the canopy.
Provide pitched roof insulation and covering: breather membrane over rafters, 150mm Ecotherm Eco-Versal insulation between rafters and 60mm below rafters to achieve 0.13 W/m2K or better, treated battens and counter battens, and 30 degree pitch concrete tiles to match existing suitable for severe exposure, re-using sound tiles salvaged from the garage roof, with ventilated ridge tiles mechanically fixed to battens and eaves ventilation trays.
Provide single-ply warm flat roof covering: vapour control layer over the plywood deck, 180mm Ecotherm Eco-Torch insulation, 50mm insulated perimeter upstand, and single-ply membrane fully adhered, to achieve 0.13 W/m2K or better.
Provide flat roof edge, verge and abutment detailing including aluminium drip flashings, box gutter, flashing strips hot welded to the membrane, and sarking membrane dressed a minimum 150mm up the rafters at the flat roof to pitched roof abutment.
Provide white UPVC fascias and soffits to the extension roofs to match existing, including insulated soffits and proprietary cross flow ventilators maintaining a minimum 25mm air gap.
Provide white UPVC gutters and downpipes to the new extension roofs and alter existing rainwater goods where affected.
Provisional: supply and install the roof integrated photovoltaic panel array to the extension pitched roof as shown on the proposed roof plan and elevations, including inverter, isolators, DC and AC wiring and commissioning.
12 | CARPENTRY
Provide internal door casings and linings to all new internal door openings: bedroom 4, en-suite, utility/plant, store, dining room, porches and link, and to the re-formed hall openings, and hang the new door leaves.
Allow an editable PC sum of £[enter amount] for the supply of the internal door leaves to all new and replacement internal doors identified on the drawings, and fit complete. Note: all existing internal doors are to be replaced.
Allow an editable PC sum of £[enter amount] for the supply of door furniture to all new internal doors, and fit complete.
Provide new skirtings and architraves to the new extensions and to the internally re-planned areas of the existing house, new and disturbed areas only.
Provide window boards to all new windows in the extensions and to the existing windows where the external wall insulation reveals are altered, including 25mm rigid insulation under the board.
Provide timber boxing to exposed steelwork and general boxing to services and soil pipes.
Provide the joinery to the window hatch shown between the kitchen and dining area on the proposed ground floor plan.
13 | SERVICES
Carry out a full electrical rewire of the existing house and new extensions, including new consumer unit, sockets, switches, lighting circuits, earthing and bonding, all to BS 7671:2018 (Amendment 2:2022) and Approved Document P, and provide Electrical Installation Certificates, permanent labelling, operating instructions and as-installed layout drawings on completion.
Supply and install a Grade D1, Category LD2 mains powered interlinked smoke alarm system with tamper-proof battery back-up to BS 5839-6:2019, with heat alarm to the kitchen and carbon monoxide detectors to rooms containing fixed fuel burning appliances.
Supply and install 1 no. electric vehicle charging point at the parking area as shown on the proposed site plan, including supply cabling and protective devices.
Replace the existing oil boiler with a new boiler, including new flue, controls, connection to the existing oil supply and commissioning.
Replace the existing cold water storage tank in the loft, including insulation, overflow and connections.
Provide underfloor heating to the extensions, including manifold, zone controls, pipework connection to the heat source, balancing and commissioning.
Provide plumbing and above ground waste installation to the new en-suite, utility and refitted bathroom, including 32mm basin, 40mm sink and 110mm WC wastes at a minimum fall of 1:55, brackets at maximum 600mm centres and rodding access at all bends, to BS EN 12056-2 and Approved Document H.
Allow an editable PC sum of £[enter amount] for the supply of sanitaryware, brassware and accessories to the new en-suite, and install complete.
Allow an editable PC sum of £[enter amount] for the supply of sanitaryware, brassware and accessories to the refitted bathroom, and install complete.
Provide mechanical extract ventilation to Approved Document F: 30 l/s above the hob (or 60 l/s elsewhere) to the kitchen using the existing capped chimney as the extract route, 30 l/s to the utility, 15 l/s to the bathroom and en-suite, and 10mm undercuts to internal doors.
Provisional: supply and install an air source heat pump in the position shown on the proposed ground floor plan, including base, pipework, buffer/cylinder connections, electrical supply and commissioning. Note: only recommended by the designer if the external wall insulation is installed.
Provisional: supply and install a whole house mechanical ventilation with heat recovery system in place of the intermittent extract, including unit, ductwork, terminals and commissioning.
14 | INTERNAL FINISHES
Provide plasterboard and plaster skim to the new extension walls, ceilings and vaulted roof slopes, including vapour control layers, optional 25mm timber battened service voids where required, beads and tapes.
Prepare and bring up to an internal plaster skimmed standard the previously external walls of the existing house now enclosed by the dining room extension, the link and the porches, including local removal of unsuitable external render, dubbing out and levelling, suitable plaster background, beads, making good and skim.
Provide 30 minute fire rated plasterboard encasement or intumescent paint to all new structural steelwork.
Make good all disturbed plasterwork to the existing house arising from the demolition of partitions, the chimney breast removal, the new openings and the blocked up openings.
Provide waterproof tanking to the wet areas of the new en-suite and the refitted bathroom, and wall and floor tiling complete.
Supply and lay Amtico luxury vinyl flooring to the new dining room over the underfloor heating.
Provisional: supply and lay floor finishes to bedroom 4, en-suite, utility/plant, store, link and porches. Final selections are to be confirmed by the client.
Provide floor finishes to the re-planned areas of the existing house disturbed by the works, including the kitchen, hall and bathroom.
Decorate the new extensions throughout and all new and disturbed areas of the existing house, including two coats of emulsion to walls and ceilings and painting to all new joinery.
15 | EXTERNAL FINISHES
Provide 3 coat polymer render system to the new rendered blockwork extension walls, including beads, stop beads and drips.
Provide vertical grey fibre cement cladding to the extension and porch walls, fixed to treated timber battens on treated counter battens over a windtight breather membrane, including fibre cement reveals and metal drip flashings fixed to the blockwork.
Provide 30 minute intumescent fire rated cavity barriers to the ventilated rainscreen cavity at the base above DPC/starter track, around all window and door openings, 300mm from corner walls, at eaves level and around all penetrations, and insect mesh to all cladding cavity openings.
Provide insulated cavity closers (30 minute fire rated), cavity trays, weep holes and flexible Rockwool to reduce thermal bridging at all openings and wall/roof junctions.
Provide masonry brick plinth to the extension as shown on the proposed detail sections and elevations.
Provisional: install rendered external wall insulation to the existing house walls: remove or smooth out existing render, 100mm Weber mineral wool EWI insulation adhered with adhesive mortar, plastic starter track, 50mm XPS plinth board, high polymer base coat, reinforcing mesh, silicone primer and silicone render, to achieve 0.21 W/m2K, including extending the existing roof over the insulation, trimming rafters, extended counter battens and re-fixed fascias, insulated reveals and sills, and 350mm Rockwool insulation between and over the existing loft joists to achieve 0.13 W/m2K.
Build the rendered twin blockwork patio wall / raised planter walls with wall ties at 450mm vertical x 750-900mm horizontal centres, and lay composite decking on suspended timber joists to the patio with a 10mm gap at the wall, threshold and decking junctions.
Build the garden walls and planters shown on the proposed ground floor plan using the stone retained from the demolished garage.
Re-lay the salvaged patio paving and make good the parking area and landscaping disturbed by the works, allowing for additional matching material as required.
Supply and fix the biodiversity features shown on the elevations: 2 no. Type 24 Schwegler bird boxes and 1 no. Beaumaris 'midi' bat box.
Supply and plant 3 no. native trees (silver birch, hazel, rowan, wild cherry, holly or quickbeam) in the positions shown on the proposed ground floor plan, including stakes, ties and mulch.
16 | FIXTURES & FITTINGS
Allow an editable PC sum of £[enter amount] for the supply of kitchen units, worktops, sink and appliances to the re-planned kitchen. Final selections to be confirmed by the client.
Allow an editable PC sum of £[enter amount] for the supply of utility room fittings, worktop and sink. Final selections to be confirmed by the client.
Allow an editable PC sum of £[enter amount] for the supply of the fitted seat / storage units shown to the dining room and link on the proposed ground floor plan, and install complete.